## Services Offered
SID | Service Title | Service Description
S1 | User Database Service | Store usernames, passwords, user portfolios, etc.
S2 | Stock Analysis Service | Fetch standard market indicators and exposes them via API. Display in an interface for stock analysis.
S3 | Market News and Sentiment Service | Fetch market news and sentiment and exposes them via API. Display in an interface for market research.
S4 | Portfolio Management Service | Allows users to insert, delete, modify their stock positions. Persistent data storage for user portfolios. | Database
S5 | Alert and Notification Service | Sends event-driven alerts (price, risk) to users via email/SMS based on portfolio or market triggers.
S6 | Earnings Call Service | Fetch earnings call statements and exposes them via API. Display in an interface for market research.

## Service Functional Requirements
SID | Service Name | FID | Requirement Description
S1 | User Database Service | FR1_1 | Store user authentication data (username, password, email, etc.).​
S1 | User Database Service | FR1_2 | Store user portfolios and track personal holdings.​
S1 | User Database Service | FR1_3 | Expose secure API endpoints for other microservices (e.g., portfolio, alert, analysis).
S2 | Stock Analysis Service | FR2_1 | Fetch and calculate technical indicators (e.g., RSI, MACD, Moving Averages).​
S2 | Stock Analysis Service | FR2_2 | Provide an interface allowing users to select stocks and view performance metrics.​
S3 | Market News and Sentiment Service | FR3_1 | Fetch financial news articles and social media posts via external APIs.​
S3 | Market News and Sentiment Service | FR3_2 | Allow sorting and filtering by relevance, date, and sentiment.​
S4 | Portfolio Management Service | FR4_1 | Store user portfolios and track personal holdings.​
S4 | Portfolio Management Service | FR4_2 | Provide dashboard APIs showing portfolio performance and P&L.​
S5 | Alert and Notification Service​ | FR5_1 | Allow users to create alerts for price thresholds and other triggers.​
S5 | Alert and Notification Service​ | FR5_2 | Trigger notifications when thresholds are met and access relevant portfolio data.​
S5 | Alert and Notification Service​ | FR5_3 | Send alerts via email.​
S6 | Earnings Call Service​ | FR6_1 | Fetch earnings call Q&A based on quarter and stock.​
S6 | Earnings Call Service​ | FR6_2 | Allow sorting by relevance and date.​

## Service Quality Requirements
SID | Service Name | QID | Requirement Description
S1 | User Database Service | QR1_1 | Database needs to be readily available.​
S1 | User Database Service | QR1_2 | User-specific information must be secure and not viewable by others.​
S1 | User Database Service | QR1_3 | Passwords are encrypted.​
S2 | Stock Analysis Service | QR2_1 | Interface includes all graphs and metrics within one page.​
S2 | Stock Analysis Service | QR2_2 | Information must be correct and reliable for the given date range.​
S2 | Stock Analysis Service | QR2_3 | Data refresh speed under 2 seconds when loading a new stock.​
S3 | Market News and Sentiment Service | QR3_1 | Sentiment accuracy of at least 90% based on validation samples.​
S3 | Market News and Sentiment Service | QR3_2 | Sentiments must be visually digestible (multiple results visible per screen).​
S3 | Market News and Sentiment Service | QR3_3 | Ensure high reliability and data freshness from APIs.​
S4 | Portfolio Management Service | QR4_1 | Users can manage portfolios efficiently (insert/delete/update).​
S4 | Portfolio Management Service | QR4_2 | Guarantee data consistency.,​
S4 | Portfolio Management Service | QR4_3 | Ensure secure data access for each authenticated user.​
S5 | Alert and Notification Service​ | QR5_1 | Deliver notifications within 10 seconds of trigger event.​
S5 | Alert and Notification Service​ | QR5_2 | Retry failed notifications up to three times.​
S5 | Alert and Notification Service​ | QR5_3 | Comply with IBM Cloud privacy and security standards.​
S6 | Earnings Call Service​ | QR6_1 | High data accuracy and timely updates.​
S6 | Earnings Call Service​ | QR6_2 | Ensure efficient API response within 2 seconds.​
​

## Arch. Significant Requirements
ASR_ID | Description | Why Architecturally Significant
ASR1 | High scalability via Kafka/Event Streams | Impacts message-driven architecture and service decoupling
ASR2 | Data persistence redundancy (Db2 + COS + Cloudant) | Determines storage architecture, backup, and disaster recovery mechanisms
ASR3 | Authentication and access control (App ID + JWT) | Influences security boundaries, API design, and gateway configuration
ASR4 | Low latency requirements (<500 ms APIs) | Affects deployment topology, choice of load balancing, and caching strategy
ASR5 | Fault tolerance and retry logic | Shapes resilience patterns (circuit breaker, retry queues, idempotent operations)
ASR6 | Event-driven alert system | Drives asynchronous architecture using IBM Cloud Functions and Event Streams

## Project Iteration Plan
Iteration | Task | Start Date | Duration (days) | Assigned To | Status
1 | Data Ingestion | 2025-10-14 | 12 |  | In Progress
1 | User/Auth | 2025-10-14 | 12 |  | In Progress
2 | Data Cleaning | 2025-10-26 | 14 |  | Not Started
2 | Fundamental Data | 2025-10-26 | 14 |  | Not Started
3 | Technical Indicators | 2025-11-09 | 12 |  | Not Started
3 | Sentiment Service | 2025-11-09 | 12 |  | Not Started
4 | Portfolio | 2025-11-21 | 13 |  | Not Started
4 | Alert/Notification | 2025-11-21 | 13 |  | Not Started
4 | API Gateway | 2025-11-21 | 13 |  | Not Started
| oct.14---oct.19 |  | oct.20---oct.26 |  | oct.27---nov.2 | nov.3---nov.9 | nov.10---nov.16 | nov.17---nov.23 | nov.24---nov.30
Data Ingestion
User/Auth
Data Cleaning
Fundamental Data
Technical Indicators
Sentiment Service
Portfolio
Alert/Notification
API Gateway

## IBM Cloud Development
SID | IBM Cloud Deployment
S1 | Databases for PostgreSQL or Cloudant (data storage)​, IBM App ID (authentication)​, IBM API Connect (endpoint management)
S2 | IBM Code Engine (analysis API runtime)​, IBM Event Streams (real-time updates)​, IBM Cloud Object Storage (historical data storage)​
S3 | IBM Code Engine (data fetch and API exposure)​, Watson NLU or Watson Discovery (sentiment and NLP analysis)​, IBM Cloud Object Storage (data caching)
S4 | IBM Code Engine (backend service)​, IBM Db2 on Cloud (transactional database)​, IBM API Connect (dashboard API management)
S5 | IBM Event Streams (Kafka) (trigger events)​, IBM Functions (serverless event handling)​, IBM Cloud Notifications or SendGrid integration (message delivery)
S6 | IBM Code Engine (data fetch and processing)​, IBM Cloud Object Storage (transcript storage)​, Watson Discovery (relevance ranking and search)

## Microservice_IBM_Cloud_Exp
Group Member | IBM Cloud Experience | MicroService Experience
Connor Courville | Limited experience with IBM Cloud platform. Mostly familiarizing myself through this project and extracurricular research. | Experienced in database design, semantic model design, data querying. Microservice architecture is a new concept to me.
Harjap Grewal | No experience in cloud technologies. First time through this project. | Experienced in database design and construction. Backend coding, UML diagram, and project design.
Yuan Zhang | No experiecne beofre | Experienced in database construction, front-end / back-end coding. Experienced in learning stock analysis. (Minoring in Economics)
Shikhar Srivastava | Experienced with AWS, but wanted to learn IBM Cloud. Can map AWS cloud services to similar IBM Cloud Services. | Experienced in building UI for automating several python workflows, gained this experience during 16 month internship at Carfax.
Mian Abdullah Zahid | Experienced with AWS and willing to learn IBM Cloud. | Experienced in building different micoservices architecture along with database design, api creation and communication.